## Sprint i
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
7 | As the parent of a picky eater, I would like to be able to mark down my son’s favorite recipes, so that I can quickly access them. | 1.) Create favorites list to hold favorited recipes. 2.) Create favorite button to add a recipe to favorites list. | 1 (Pushed to sprint 3 due to slowed development) | We want to implement a favorites system for recipes. | FR | 3 | 1 | Joe B. - 25% Helped with Project Development and Troubleshooting, Created Analysis Diagrams Odin Y. - 20% Created HTML pages for UI (Login, Home page) Raist C. - 15% Managed backlogs for sprint 3, Created Analysis Diagrams Oz C. - 15% Created original backlog, UI mockups Dylan A. - 25% Implementing UI
9 | As a person who is trying to diet, I would like to be able to see the calorie count on recipes, so I can see which ones are better for my diet. | 1.) Implement calories per serving field on recipe page. | 1 (Pushed to sprint 3 due to slowed development) | We want to implement a calorie count system for recipes. | FR | 5 | 1 | Joe B. - 25% Helped with Project Development and Troubleshooting, Created Analysis Diagrams Odin Y. - 20% Created HTML pages for UI (Login, Home page) Raist C. - 15% Managed backlogs for sprint 3, Created Analysis Diagrams Oz C. - 15% Created original backlog, UI mockups Dylan A. - 25% Implementing UI
14 | As a new cook, I would like to have step-by-step instructions for how to prepare the meal. | 1.) Implement directions (body text) field on recipe page. | 1 (Pushed to sprint 3 due to slowed development) | We want to implement a system to create directions for recipes. | FR | 3 | 1 | Joe B. - 25% Helped with Project Development and Troubleshooting, Created Analysis Diagrams Odin Y. - 20% Created HTML pages for UI (Login, Home page) Raist C. - 15% Managed backlogs for sprint 3, Created Analysis Diagrams Oz C. - 15% Created original backlog, UI mockups Dylan A. - 25% Implementing UI
6 | As a person with limited internet access, I would like to be able to download recipes, so that I can use them without being connected to the internet. | 1.) Implement a download feature. 2.) Implement the ability to use the app offline | 2 (Pushed to sprint 3 due to slowed development) | We want to make it so people can download recipes for when they cannot connect to the internet. | FR | 3 | 1 | Joe B. - 25% Helped with Project Development and Troubleshooting, Created Analysis Diagrams Odin Y. - 20% Created HTML pages for UI (Login, Home page) Raist C. - 15% Managed backlogs for sprint 3, Created Analysis Diagrams Oz C. - 15% Created original backlog, UI mockups Dylan A. - 25% Implementing UI
8 | As a European, I would like to be able to have units of measurement be converted automatically, so that I don’t have to spend time converting them myself. | 1.) Implement a feature that converts units from imperial to metric | 2 (Pushed to sprint 3 due to slowed development) | We want the ability to switch between two different measuring units. | FR | 3 | 1 | Joe B. - 25% Helped with Project Development and Troubleshooting, Created Analysis Diagrams Odin Y. - 20% Created HTML pages for UI (Login, Home page) Raist C. - 15% Managed backlogs for sprint 3, Created Analysis Diagrams Oz C. - 15% Created original backlog, UI mockups Dylan A. - 25% Implementing UI
12 | As someone who doesn’t like to spend a lot of time cooking, I would like an estimated cook/prep time for a recipe, so I can avoid recipes that might take too long to make. | 1.) Implement an estimated time slot for users to fill in when creating the recipes | 2 (Pushed to sprint 3 due to slowed development) | We want users to have the ability to input the estimated cook/prep time for their recipes. | FR | 3 | 1 | Joe B. - 25% Helped with Project Development and Troubleshooting, Created Analysis Diagrams Odin Y. - 20% Created HTML pages for UI (Login, Home page) Raist C. - 15% Managed backlogs for sprint 3, Created Analysis Diagrams Oz C. - 15% Created original backlog, UI mockups Dylan A. - 25% Implementing UI