## Sheet1
ID | User Story | Sprint Number | Story Priority | Story Status | Story Points
1 | As a college student with a limited income, I would like the ability to search for recipes via ingredients, so I can use what I have to cook my meals | Sprint 4 | 3 | W | 13
2 | As a stay-at-home dad, I would like the ability to search for recipes that make many portions would be great, so I can select meals that can feed all my kids. | Sprint 4 | 8 | W | 5
3 | As a person who loves cultural cuisine, I would like the ability to search for recipes via culture, so I can discover recipes from different cultures. | Sprint 4 | 13 | W | 8
4 | As a visually impaired user, I would like to have descriptive alt-text for photos of meals would be amazing, as it would allow me to gain a better understanding of the food I would like to have prepared. | Sprint 5+ | 16 | W | 8
5 | As a person with allergies, I would like to be able to exclude certain ingredients from my search results, so that I can avoid foods that include ingredients that I am allergic to. | Sprint 4 | 7 | W | 8
6 | As a person with limited internet access, I would like to be able to download recipes, so that I can use them without being connected to the internet. | Sprint 2 | 11 | IP | 8
7 | As the parent of a picky eater, I would like to be able to mark down my son’s favorite recipes, so that I can quickly access them. | Sprint 1 | 4 | IP | 3
8 | As a European, I would like to be able to have units of measurement be converted automatically, so that I don’t have to spend time converting them myself. | Sprint 2 | 5 | IP | 5
9 | As a person who is trying to diet, I would like to be able to see the calorie count on recipes, so I can see which ones are better for my diet. | Sprint 1 | 2 | IP | 5
10 | As someone who might have similar ingredients but not the exact ones for a recipe, I would like to be able to see valid substitutions, so I don’t have to buy extra ingredients. | Sprint 5 | 9 | W | 13
11 | As a chef, I would like a commenting system, so people can critique my ideas. | Sprint 5 | 6 | W | 8
12 | As someone who doesn’t like to spend a lot of time cooking, I would like an estimated cook/prep time for a recipe, so I can avoid recipes that might take too long to make. | Sprint 2 | 12 | IP | 5
13 | As a person with celiac disease, I would like to be able to filter out recipes so I can cook gluten free. | Sprint 4 | 10 | W | 5
14 | As a new cook, I would like to have step-by-step instructions for how to prepare the meal. | Sprint 1 | 1 | IP | 3
15 | As a stay at home mom, I would like to have a map feature that shows local grocery stores with the ingredients I am looking for. | Sprint 5+ | 15 | W | 13
16 | As a social media enthusiast, I would like to have user profiles so I can see recipes each person may have created and they can see mine as well. | Sprint 5+ | 14 | W | 13
17 | As a diabetic, I would like to know how much sugar is in the recipes I find online so I can make sure that I am consuming a safe amount of sugar. | Sprint 5 | 17 | W | 8
18
19
20