## Sprint i
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
7 | As the parent of a picky eater, I would like to be able to mark down my son’s favorite recipes, so that I can quickly access them. | 1.) Create favorites list to hold favorited recipes. 2.) Create favorite button to add a recipe to favorites list. | 1 | We want to implement a favorites system for recipes. | FR | 3 | 1 | Joe B. - 50%, set up template project files to begin developing systems. Odin Y. - 50%, selected user stories for this sprint.
9 | As a person who is trying to diet, I would like to be able to see the calorie count on recipes, so I can see which ones are better for my diet. | 1.) Implement calories per serving field on recipe page. | 1 | We want to implement a calorie count system for recipes. | FR | 5 | 1 | Joe B. - 50%, set up template project files to begin developing systems. Odin Y. - 50%, selected user stories for this sprint.
14 | As a new cook, I would like to have step-by-step instructions for how to prepare the meal. | 1.) Implement directions (body text) field on recipe page. | 1 | We want to implement a system to create directions for recipes. | FR | 3 | 1 | Joe B. - 50%, set up template project files to begin developing systems. Odin Y. - 50%, selected user stories for this sprint.