## Sprint i
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
7 | As the parent of a picky eater, I would like to be able to mark down my son’s favorite recipes, so that I can quickly access them. | 1.) Create favorites list to hold favorited recipes. 2.) Create favorite button to add a recipe to favorites list. | 1 | We want to implement a favorites system for recipes. | FR | 3 | 1 | Joe B. - 20% Worked on use case-based testing Odin Y. - 20% Worked on Front end Web Development and updated project documents Raist C. - 20% Worked on plan for the future document and updated other project documents Oz C. - 20% Worked on unit testing and usability study document Dylan A. - 20% Worked on unit testing
9 | As a person who is trying to diet, I would like to be able to see the calorie count on recipes, so I can see which ones are better for my diet. | 1.) Implement calories per serving field on recipe page. | 1 | We want to implement a calorie count system for recipes. | FR | 5 | 1 | Joe B. - 20% Worked on use case-based testing Odin Y. - 20% Worked on Front end Web Development and updated project documents Raist C. - 20% Worked on plan for the future document and updated other project documents Oz C. - 20% Worked on unit testing and usability study document Dylan A. - 20% Worked on unit testing
14 | As a new cook, I would like to have step-by-step instructions for how to prepare the meal. | 1.) Implement directions (body text) field on recipe page. | 1 | We want to implement a system to create directions for recipes. | FR | 3 | 1 | Joe B. - 20% Worked on use case-based testing Odin Y. - 20% Worked on Front end Web Development and updated project documents Raist C. - 20% Worked on plan for the future document and updated other project documents Oz C. - 20% Worked on unit testing and usability study document Dylan A. - 20% Worked on unit testing
6 | As a person with limited internet access, I would like to be able to download recipes, so that I can use them without being connected to the internet. | 1.) Implement a download feature. 2.) Implement the ability to use the app offline | 2 | We want to make it so people can download recipes for when they cannot connect to the internet. | FR | 3 | 1 | Joe B. - 20% Worked on use case-based testing Odin Y. - 20% Worked on Front end Web Development and updated project documents Raist C. - 20% Worked on plan for the future document and updated other project documents Oz C. - 20% Worked on unit testing and usability study document Dylan A. - 20% Worked on unit testing
8 | As a European, I would like to be able to have units of measurement be converted automatically, so that I don’t have to spend time converting them myself. | 1.) Implement a feature that converts units from imperial to metric | 2 | We want the ability to switch between two different measuring units. | FR | 3 | 1 | Joe B. - 20% Worked on use case-based testing Odin Y. - 20% Worked on Front end Web Development and updated project documents Raist C. - 20% Worked on plan for the future document and updated other project documents Oz C. - 20% Worked on unit testing and usability study document Dylan A. - 20% Worked on unit testing
12 | As someone who doesn’t like to spend a lot of time cooking, I would like an estimated cook/prep time for a recipe, so I can avoid recipes that might take too long to make. | 1.) Implement an estimated time slot for users to fill in when creating the recipes | 2 | We want users to have the ability to input the estimated cook/prep time for their recipes. | FR | 3 | 1 | Joe B. - 20% Worked on use case-based testing Odin Y. - 20% Worked on Front end Web Development and updated project documents Raist C. - 20% Worked on plan for the future document and updated other project documents Oz C. - 20% Worked on unit testing and usability study document Dylan A. - 20% Worked on unit testing
1 | As a college student with a limited income, I would like the ability to search for recipes via ingredients, so I can use what I have to cook my meals | 1.) Search for recipes via ingredients | 3 | We want users to have the ability to search for recipes based on ingredients they have in their homes. | FR | 3 | 1 | Joe B. - 20% Worked on use case-based testing Odin Y. - 20% Worked on Front end Web Development and updated project documents Raist C. - 20% Worked on plan for the future document and updated other project documents Oz C. - 20% Worked on unit testing and usability study document Dylan A. - 20% Worked on unit testing
2 | As a stay-at-home dad, I would like the ability to search for recipes that make many portions would be great, so I can select meals that can feed all my kids. | 1.) Search for recipes via the amounts of portions they make. | 3 | We want users to be able to search for recipes based on portion sizes. | FR | 3 | 1 | Joe B. - 20% Worked on use case-based testing Odin Y. - 20% Worked on Front end Web Development and updated project documents Raist C. - 20% Worked on plan for the future document and updated other project documents Oz C. - 20% Worked on unit testing and usability study document Dylan A. - 20% Worked on unit testing
3 | As a person who loves cultural cuisine, I would like the ability to search for recipes via culture, so I can discover recipes from different cultures. | 1.) Search for recipes based on cultures. | 3 | We want users to have the ability to search for recipes based on cultures from around the world. | FR | 3 | 1 | Joe B. - 20% Worked on use case-based testing Odin Y. - 20% Worked on Front end Web Development and updated project documents Raist C. - 20% Worked on plan for the future document and updated other project documents Oz C. - 20% Worked on unit testing and usability study document Dylan A. - 20% Worked on unit testing
5 | As a person with allergies, I would like to be able to exclude certain ingredients from my search results, so that I can avoid foods that include ingredients that I am allergic to. | 1.) Exclude ingredients from searches for recipes. | 4 | We want users to be able to search for recipes by excluding ingredients that they may not want. | FR | 3 | 1 | Joe B. - 20% Worked on use case-based testing Odin Y. - 20% Worked on Front end Web Development and updated project documents Raist C. - 20% Worked on plan for the future document and updated other project documents Oz C. - 20% Worked on unit testing and usability study document Dylan A. - 20% Worked on unit testing
13 | As a person with celiac disease, I would like to be able to filter out recipes so I can cook gluten free. | 1.) Search for gluten free recipes. | 4 | We want users to have the ability to search for recipes that gluten free. | FR | 3 | 1 | Joe B. - 20% Worked on use case-based testing Odin Y. - 20% Worked on Front end Web Development and updated project documents Raist C. - 20% Worked on plan for the future document and updated other project documents Oz C. - 20% Worked on unit testing and usability study document Dylan A. - 20% Worked on unit testing