## Sprint i
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
1 | As a college student with a limited income, I would like the ability to search for recipes via ingredients, so I can use what I have to cook my meals | 1.) Implement search via ingredients | 2 | We want to implement a system that allows users to search for recipes via ingredients they input. | FR | 3 | 1 | Joe B. - 20% Created a NodeJS project to start Odin Y. - 15% Updated product backlog Raist C. - 15% Contributed details for this story for this sprint Oz C. - 20% Created UI mockups Dylan A. - 20% Created UI mockups
7 | As the parent of a picky eater, I would like to be able to mark down my son’s favorite recipes, so that I can quickly access them. | 1.) Create favorites list to hold favorited recipes. 2.) Create favorite button to add a recipe to favorites list. | 1 (Continued on 2) | We want to implement a favorites system for recipes. | FR | 3 | 1 | Joe B. - 30% Created a NodeJS project to start and UI mockups Odin Y. - 15% Chose story for sprint 1 Raist C. - 15% Managed backlog for sprint 2 Oz C. - 15% Created original backlog Dylan A. - 25% Created UI mockups
9 | As a person who is trying to diet, I would like to be able to see the calorie count on recipes, so I can see which ones are better for my diet. | 1.) Implement calories per serving field on recipe page. | 1 (Continued on 2) | We want to implement a calorie count system for recipes. | FR | 5 | 1 | Joe B. - 30% Created a NodeJS project to start and UI mockups Odin Y. - 15% Chose story for sprint 1 Raist C. - 15% Created user story Oz C. - 15% Created original backlog Dylan A. - 25% Created UI mockups
14 | As a new cook, I would like to have step-by-step instructions for how to prepare the meal. | 1.) Implement directions (body text) field on recipe page. | 1 (Continued on 2) | We want to implement a system to create directions for recipes. | FR | 3 | 1 | Joe B. - 30% Created a NodeJS project to start and UI mockups Odin Y. - 15% Chose story for sprint 1 Raist C. - 15% Contributed details for this story for this sprint Oz C. - 15% Created original backlog Dylan A. - 25% Created UI mockups